## RDG Actions
ID | Suggestion | From | Date Raised | RDG Comment | Date comment added / last updated | Suggested work programme items | Date suggested WP items added / last updated | Ongoing notes
1 | Any suggestions for a highways consultant to do feasibility reports. | Restoration Panel | 2026-08-22 | None known to RDG. Share request with other groups. It would be useful to understand the scope of works and background to the request to inform other actions - e.g. is this for road realignment / new access / temporary works to facilitate canal / new bridge design etc. Nature of consultant might differ depending on answer. | 2026-08-31 | 1. Share request with other groups via bulletin / RP mailing. 2. Seek input via focussed discussion on highways to inform other actions. Consider input from Wey & Arun, Montgomery on recent highway works? 3. Investigate recent works done to highways by restoration groups, via request in bulletin / RP mailing, restoration summaries, restoration group updates and focussed discussion. | 2026-08-31
2 | Are the practical restoration handbooks available to view online? | Restoration Panel | 2026-08-22 | Yes. Visibility and organisation of all restoration supporting material needs to be reviewed on website and existence more widely published. | 2026-08-31 | 1. Share link to PRH and other documentation via bulletin / RP mailing. 2. Review documentation on website and reorganise | 2026-08-31
3 | Are we in danger of having and attending so many restoration conferences (thinking IWA, NCA, CRT) there's no time to actually do any restorations | Restoration Panel | 2026-08-22 | Noted. All events should be beneficial and support restoration groups, all groups are at liberty to decide what is useful to them of course. | 2026-08-31 | No work programme items.
4 | Briefing material on Planning 101, Acts of Parliament (TWA 01), SIs (NSI National Significant Infrastructure), SDO (Special Development Order)/DCO (Content of Development)/Planning | Restoration Panel | 2026-08-22 | This is a big topic and warrants a RP discussion to inform what restoration groups are doing and what support is wanted. Further work is required even to frame the questions: - What planning consent is required for a restoration project? - When would TWO be preferable over standard TCPA application? - Do other regimes referenced apply to restoration projects or are they ones that groups need to be aware of for intefering / supportive other projects (e.g. the White Horse Reservoir discussion)? - How do restoration groups adequately respond to planning applications, and how can the IWA planning advisory panel support? | 2026-08-31 | 1. Seek input via focussed discussion on planning approaches to inform further actions. 2. RDP engage with planning advisory panel to understand remit and scope of support / knowledge available. | 2026-08-31
5 | Bring along a Waterways MP | Restoration Panel | 2026-08-22 | Presumably this means to RP meetings? Would need to agree the purpose and scope of an MP attending and whether the RP or the conference is the best environment. There is potential benefit in inviting an MP to a focussed discussion on engaging MPs, the political process etc, but inviting them without purpose is likely pointless and runs counter to the intention of keeping the RP at a manageable size. | 2026-08-31 | 1. Engage with the proposer on the purpose of the suggestion. 2. Discuss with IWA Campaigns Director on how to engage politicians most effectively in restoration issues - potentially form this into a focussed discussion. | 2026-08-31
6 | Could NCA / IWA approach Stafford Boat Club (or other boat clubs) to see if they would host a conference. SBC has car park close to M6. Stafford is on West Coast main railway. SBC also has up to date presentation facilities, bar and kitchen | Restoration Panel | 2026-08-22 | RP chair to note for future meetings. | 2026-08-31 | No work programme items.
7 | Could universities play a larger part for example student surveys and research, | Restoration Panel | 2026-08-22 | Likely yes. This could theoretically apply at both restoration group and national level. How would universities be engaged? What is the scope of works envisaged? How do we ensure it is (a) more than 'free' work and (b) useful to the groups at the end of work? Does this apply also to other levels of education? | 2026-08-31 | 1. Investigate examples of restoration groups / IWA engaging with universities, how this was managed and how effective it was. 2. Seek input via focussed discussion to inform further actions | 2026-08-31
8 | Could we subscribe as a group to the CIRIA system for assessing benefits of canals etc | Restoration Panel | 2026-08-22 | Not familiar with CIRIA in this context, needs further investigation. | 2026-08-31 | 1. Investigate CIRIA and engage with proposer to discuss purpose. | 2026-08-31
9 | CRT seem not to want canals to be restored. They seem to actively obstruct by legal methods. | Restoration Panel | 2026-08-22 | Noted. We need further details on examples of this to determine actions, also so that we can be clear it is CRT 'at fault'. | 2026-08-31 | 1. Include within focussed CRT RDP discussion session. 2. Share general request for groups to highlight obstructions (perceived or actual) set by CRT or other agencies via bulletin / RP mailing. 3. Use highlighted obstructions to consider further actions. | 2026-08-31
10 | Current snags and hold-ups to be included in individual restoration update reports | Restoration Panel | 2026-08-22 | Noted and agreed. | 2026-08-31 | 1. Consider in restoration report scoping. | 2026-08-31
11 | Developing / sharing a common best practise planning policy would be useful | Restoration Panel | 2026-08-22 | Restoration groups cross a lot of planning authorities - reviewing existing planning policies for restoration and developing a 'best practice' could be useful to support restoration groups campaigning for increased protection. Need to seek input from planning advisory panel | 2026-08-31 | 1. Ask restoration groups to identify any good / bad planning policies that protect their restoration project - via bulletin / RP mailing. 2. RDG engage with planning advisory panel on how to proceed. 3. Seek input via focussed discussion on planning policies. | 2026-08-31
12 | Did you try to contact the Hollinwood canal society, by what means? | Restoration Panel | 2026-08-22 | For RP chair. | 2026-08-31 | No work programme items.
13 | Distances involved in attending meetings is prohibitive and expensive for some small societies with limited resources | Restoration Panel | 2026-08-22 | For RP chair to consider. | 2026-08-31 | No work programme items.
14 | Each RP meeting should have 5 or 6 presentations on a wide variety of problems and issues | Restoration Panel | 2026-08-22 | Noted. IWA wants to be careful to facilitate discussion and get input into actions for the restoration work programme, so the RP meeting programme needs to allow sufficient time for discussion on each item. | 2026-08-31 | No work programme items.
15 | FIOSH (Federal Institute for Occupational Safety and Health – Germany) have expectation to provide Pro Bono support - should explore. | Restoration Panel | 2026-08-22 | Presumably the intent of this suggestion is to understand the UK approach and where professionals in certain fields may be expected to provide some pro bono support? It would be useful to understand who currently gets pro bono support, how this was attracted etc and how useful it is. Also, when do groups believe they should start paying for services? | 2026-08-31 | 1. Engage with the proposer to discuss the intent of the suggestion. 2. Encourage sharing of experience and seek input to future action via focussed discussion. | 2026-08-31
16 | Floating solar panels for pumping | Restoration Panel | 2026-08-22 | Is this a current or proposed approach? Share for information, future actions to depend on feedback. | 2026-08-31 | 1. Engage with the proposer to clarify if this is current / proposed. 2. Share via bulletin / RP mailing. | 2026-08-31
17 | HMG -> DEFRA, Waterways Trust -> CRT. Split out restoration | Restoration Panel | 2026-08-22 | I have seen a version of this proposal before, but I am unclear on the purpose of it other than to potentially remove CRT from the restoration picture (although even that is unclear in situations like Wendover). Campaigning for such a change would require a lot of effort, so clarity of purpose and the scale of impact on the full restoration sector (not just CRT related projects) needs to be considered before taking action. | 2026-08-31 | 1. Engage with the proposer to develop a case for what the change is seeking to achieve, before setting any further actions. | 2026-08-31
18 | How about a restoration WhatsApp group to ask for help or report news | Restoration Panel | 2026-08-22 | Agreed that there needs to be something along this line. Consider what is easiest and most effective to implement and get input from groups. Not being an expert, it would be useful to understand how best to set up WhatsApp for this purpose as otherwise I can see it becoming a group people quickly mute! | 2026-08-31 | 1. Ask for input from restoration groups via bulletin / RP mailing. | 2026-08-31
19 | How does the restoration conference fit into the new picture | Restoration Panel | 2026-08-22 | It remains as a joint event between CRT & IWA and is open to more people. The form of the event will evolve in response to feedback. | 2026-08-31 | No work programme items.
20 | How many restoration groups are active and how active? | Restoration Panel | 2026-08-22 | Unknown, it is hoped that the restoration reports can rectify this. | 2026-08-31 | 1. Consider in restoration report scoping. | 2026-08-31
21 | How to deal with a small number of locals who are unhappy with our depot and want it moved | Restoration Panel | 2026-08-22 | Without knowing the details, it feels this would primarily be a knowledge sharing task, although wider lessons / actions could come out of that discussion. It would be helpful to know more details - particularly: - location / size of depot (including photos) - use of depot (purpose, regularity and timing of access etc) - legal status of land and depot (ownership / consent / conditions etc) | 2026-08-31 | 1. Engage with proposer to understand issues an background 2. Share request for help via bulletin / RP mailing 3. Facilitate discussion between groups, identify national actions if relevant | 2026-08-31
22 | How to make rivers stroke lakes navigable? | Restoration Panel | 2026-08-22 | Need to understand where this has been done and when, along with how many restoration groups are considering or actively planning doing this. What is the legislative framework and issues to consider? | 2026-08-31 | 1. Ask groups to identify if they have / are planning to do this - via bulletin / RP mailing. 2. Seek input as to issues and possible actions via focussed discussion | 2026-08-31
23 | How to negotiate for a restored independent canal to be adopted or managed in some way by CRT | Restoration Panel | 2026-08-22 | At the moment, it is very clear CRT are not going to do this. Consider how to support groups with planning for ongoing management (e.g. understanding responsibilities, costs). In the longer term, the CRT position is only likely to change if more money is available, consider this in wider IWA campaigning. | 2026-08-31 | 1. Seek input via focussed discussion on how restoration groups are / should be planning for ongoing management of restoration projects. 2. Review what existing guidance IWA has available. 3. Review what guidance other organisations have available. | 2026-08-31
24 | How will events be publisised? | Restoration Panel | 2026-08-22 | For RP chair. | 2026-08-31 | No work programme items.
25 | How will the RP work with CRT | Restoration Panel | 2026-08-22 | It isn't intended that the RP will have any direct relationship with CRT. Engagement with CRT will be via the RDG / IWA except for any specific sessions of the RP to which CRT is invited. RP members are encouraged to raise issues and suggested actions to inform RDG engagement | 2026-08-31 | No work programme items.
26 | If we are proactive in defining a national water distribution infrastructure it might avoid future WHR issues. We'd need to coordinate IWA / CRT etc inputs | Restoration Panel | 2026-08-22 | Agreed. This needs a focussed discussion to set the framework and understand actions, incorporating IWA water lead. | 2026-08-31 | 1. RDG engage with IWA water lead to discuss scope. 2. Discuss next steps in focussed discussion. | 2026-08-31
27 | Inland waterways could act as the UK Water Grid and would protect all waterways past and present | Restoration Panel | 2026-08-22 | Agreed in part - each waterway is going to have to be a genuine part of that grid to achieve the aim. Water transfer / water grid is a clear area that IWA will be seeking further thoughts / input on. | 2026-08-31 | 1. RDG engage with IWA water lead to discuss scope. 2. Discuss next steps in focussed discussion. | 2026-08-31
28 | Interaction with central government for legislation etc that isn't such a challenge for us as voluntary groups | Restoration Panel | 2026-08-22 | This will be an ongoing strand of the restoration work programme, but needs specific input from restoration groups to identify what legislation is challenging and how it could be amended. | 2026-08-31 | 1. Seek suggestions for 'challenging legislation' items from restoration groups. 2. Discuss possible changes in focussed discussion(s) | 2026-08-31
29 | Is work to restore our waterways for navigation already stated as our key activity and our priority? Does our constitution make that clear? | Restoration Panel | 2026-08-22 | This is for individual restoration groups to assess - the IWA is not interested in regulating restoration groups or seeking to define their purpose. Restoration to non-navigable uses may be equally valid. | 2026-08-31 | No work programme items.
30 | It is important to provide a resource and network for those that want it and not try to regulate all restorations | Restoration Panel | 2026-08-22 | Agreed. The RP aims to seek as representative an input as possible and to be able to facilitate / circulate as widely as possible, but it recognises that it can only engage with groups that wish to engage (and see the benefit of doing so). | 2026-08-31 | No work programme items.
31 | It would be useful to know what specialities each attendee possesses and how they could contribute to restoration. | Restoration Panel | 2026-08-22 | The restoration reports will start to address this. RDG will discuss whether further actions are needed / beneficial. | 2026-08-31 | 1. Consider in restoration report scoping. | 2026-08-31
32 | IWA ought to consider the benefits of monitoring of works completed | Restoration Panel | 2026-08-22 | Monitoring of completed / ongoing projects. Post completion evaluation was done of K&A, HNC etc by BW, but what has happened since? Review evaluation to date, what would be beneficial etc. | 2026-08-31 | 1. Review previous work done to monitor the benefits of completed canals 2. Seek input via focussed discussion on what data what support groups 3. Engage with IWA campaigns director for advice / scoping | 2026-08-31
33 | IWA should look at TWO guidance for groups | Restoration Panel | 2026-08-22 | Review what guidance is already in place - MKP seemed convinced something was published by IWA several years ago, but I can't recall this. Need to understand how many groups are thinking / ought to be thinking about this and what common support could be given to groups. | 2026-08-31 | 1. Review existing guidance. 2. Identify groups considering TWO 3. Put on introductory session with parliamentary agent & Geoff Pursglove. 4. Seek input as to support / guidance needed via focussed discussion | 2026-08-31
34 | IWA visits to restoration projects, would this be useful for people to see issues on site? | Restoration Panel | 2026-08-22 | This is done by NCA at present, so the RP would only put on visits where there is a specific request / issue that would benefit from it. | 2026-08-31 | No work programme items.
35 | Moving from primary focus on restoration to primary focus on management maintenance and operation | Restoration Panel | 2026-08-22 | See item 23 above. | 2026-08-31 | See item 23 above. | 2026-08-31
36 | Need for open forum such as WhatsApp or similar | Restoration Panel | 2026-08-22 | See item 18 above. | 2026-08-31 | See item 18 above. | 2026-08-31
37 | Not a major point but to be aware that the position in Wales and Scotland is different. EA is England only, politics in Wales is totally different and more accessible. | Restoration Panel | 2026-08-22 | Noted. RDG needs to better understand this, the scope of restoration activities in Wales and Scotland, and will consider separate engagement with those restoration groups to understand where relevant. | 2026-08-31 | 1. Understand scope of restoration activity in Wales & Scotland. 2. Engage with restoration groups in devolved regions to understand potential differences. | 2026-08-31
38 | NSIPs (National Significant Infrastructure Projects) are good if they include canals and their restoration. | Restoration Panel | 2026-08-22 | Not clear on what the action is here. | 2026-08-31 | 1. Engage with the proposer to discuss the purpose of the comment. | 2026-08-31
39 | Ofwat (Water Services Regulation Authority ) Funding via URMP29 (Urban Rivers Management Plan) etc | Restoration Panel | 2026-08-22 | Consider within work strand on water transfer. | 2026-08-31 | 1. Engage with the proposer to discuss the purpose of the comment. | 2026-08-31
40 | Parliamentary Engagement / APPG (All-Party Parliamentary Group) | Restoration Panel | 2026-08-22 | Multiple strands to consider here about purpose and methods of parliamentary engagement (and wider political engagement) - e.g. engaging for local group benefit, engaging on national issues, changing legislation etc. | 2026-08-31 | 1. RDG engage with IWA Campaigns Director for advice on this. 2. Focussed discussion on purpose and methodology for political engagement. 3. Understand APPG frequency, agenda and outputs. | 2026-08-31
41 | Please do not make anything online exclusive not everyone has a smartphone or is computer literate, particularly older volunteers. | Restoration Panel | 2026-08-22 | Noted. We will do our best to make everything as available as possible but have to recognise that online meetings will be essential if we are to facilitate regular meaningful discussion without everybody travelling long distances (which is equally prohibitive to many). We hope groups can identify people who are able to attend such sessions and distribute internally to others. | 2026-08-31 | No work programme items.
42 | Presentation on how to identify a water transfer opportunity would be of potential interest to lots of societies | Restoration Panel | 2026-08-22 | Consider within work strand on water transfer. It would be beneficial to look at how groups move from 'I've heard that canals can be good for water transfer' to 'my canal could specifically address this water need'. | 2026-08-31 | 1. Seek input from groups actively involved in this area to discuss how water transfer opportunities have been identified. | 2026-08-31
43 | Public Domain Info is good, but how about a closed group share with Northern Canals Association | Restoration Panel | 2026-08-22 | Keep under review depending on what is to be shared. | 2026-08-31 | No work programme items.
44 | Should cover Governance e.g. Construction (Design and Management), liability, regulation of waterways | Restoration Panel | 2026-08-22 | Noted. RDG & RP will consider all topics for discussion, the only caveat is that they must be relevant to restoration groups. | 2026-08-31 | No work programme items.
45 | Should IWA contact restoration groups directly regarding CDM to let them know that it is not optional | Restoration Panel | 2026-08-22 | Keep under review - we want to support groups and if this warrants occasional 'home truths' then we would consider. In the context of CDM, we are reviewing the outputs from the CDM discussion at the RP in more detail and will determine work actions shortly. | 2026-08-31 | 1. Incorporate work programme items from CDM session at RP 22/08/26. | 2026-08-31
46 | Systems to record training and activities | Restoration Panel | 2026-08-22 | I presume this mainly relates to the insurance questionnaire? Engage further with the proposer to identify the issue / opportunity and potential actions. | 2026-08-31 | 1. Engage with the proposer to discuss purpose and possible actions. | 2026-08-31
47 | TWAO (Transport and Works Act Order) happy to share, progress so far | Restoration Panel | 2026-08-22 | Noted - consider alongside item 33 above. | 2026-08-31 | See item 33 above. | 2026-08-31
48 | We have mostly travelled, should be a longer session | Restoration Panel | 2026-08-22 | Noted. RP will seek feedback and evolve as relevant. | 2026-08-31 | 1. RP to seek feedback on the first session - duration, location etc. | 2026-08-31
49 | We need a library of standard designs (with caveats if necessary) for components of canals for example locks, towpath walls, bywashs, etc | Restoration Panel | 2026-08-22 | This is a topic that always sounds easy on paper and is really difficult in practice. However, there should be more that can be done on components and on specifications / AiPs etc. | 2026-08-31 | 1. RDG to seek input from hon engineers. 2. Arrange focussed discussion with engineering leads from restoration groups to identify common designs / scoping documents etc. | 2026-08-31
50 | We need to change the negativity that we use to talk about CRT / EA | Restoration Panel | 2026-08-22 | RDG to discuss how this could be achieved and whether it is a useful aim. | 2026-08-31 | 1. RDG to discuss | 2026-08-31
51 | We should report issues and achievements and opportunities rather than a static “this is where we are” | Restoration Panel | 2026-08-22 | Agreed - purpose of restoration reports to be about sharing challenges / opportunities / achievements for common learning etc. | 2026-08-31 | 1. Consider in restoration report scoping. | 2026-08-31
52 | What frequency should RP session be - one per month in months when other activities are not happeneing (NCA, Conf etc) | Restoration Panel | 2026-08-22 | Noted. RP will seek feedback and evolve as relevant. | 2026-08-31 | 1. RP to seek feedback on the first session - duration, location etc. | 2026-08-31
53 | What is the average membership fee required by societies? Ours is £10 for individuals, £12 for couples by standing order. We issue four magazines a year. | Restoration Panel | 2026-08-22 | I don't know. This would be an interesting comparison to do, but perhaps should be done alongside a discussion on the purpose of membership to both the group and the member, and the consequent benefits etc. E.g. is the purpose to register supporters (in which case, keep the membership fee low?), to create income (raise the fee?) or something else. | 2026-08-31 | 1. Research existing membership fees and benefits. 2. Discuss purpose of membership and relation to membership fees | 2026-08-31
54 | Small grants | Email after RP | 2026-08-25 | RDG has been asked by IWA finance committee to look at this with a view to utilising some of the IWA restricted funds. The size and scope of this is to be agreed. | 2026-08-31 | 1. RDG to discuss | 2026-08-31
55 | Prioritisation | Email after RP | 2026-08-25 | Prioritisation of what? IWA has a longstanding policy of not prioritising any restoration project over another, and this is not likely to change. | 2026-08-31 | 1. Engage with proposer to understand the intent of the suggestion. | 2026-08-31
56 | Encouraging WRG regional teams towards projects with particular and immediate needs | Email after RP | 2026-08-25 | Raise with WRG. Note that WRG regional groups and canal camps generally go where they invited to go, and where projects are ready to host them. | 2026-08-31 | 1. Ask WRG for feedback on this question. | 2026-08-31
57 | Civil engineering expertise | Email after RP | 2026-08-25 | Specific requests can be circulated via the bulletin / RP mailing and to the IWA honorary engineers. We don't have the resources to do any more than this, but note also item 49 above. If there is a case for IWA to commission work that would benefit multiple groups, this could be considered. | 2026-08-31 | No work programme items.
58 | Professional indemnity insurance | Email after RP | 2026-08-25 | Professional indemnity can be provided to volunteers in some circumstances, subject to a premium being paid by the restoration group. Requests are currently considered on an individual basis. | 2026-08-31 | No work programme items.
59 | IWA members, selected on geography, being directly encourage to help their local restoration group | Email after RP | 2026-08-25 | This can be done via the IWA branches and regions, and the RDG can coordinate requests for specific asks to be included in existing mailings. IWA does not have the resource to build alternative mailing list based on geography / post code (communicated to proposer 29/08/26) Consider how to more generally encourage IWA members to support local restorationg groups and how to ensure restoration groups can utilise such support. | 2026-08-31 | 1. Focussed discussion on engaging members (attracting them and retaining them). | 2026-08-31
60 | IWA branches running work parties | Email after RP | 2026-08-25 | This is for individual branches to consider. If there are specific actions that RDG could take to support this, they should be submitted for consideration in the work programme. | 2026-08-31 | No work programme items.
61 | Site visits by members of the Panel and sharing of observations with leaders of those projects | Email after RP | 2026-08-25 | See item 34 above. RDG and the new IWA Waterways Restoration Officer may undertake visits to inform the restoration work programme, but it is not intended that these will form any sort of 'audit' unless requested by the group being visited. | 2026-08-31 | No work programme items.
62 | Nominating trustees to the boards of members of the Panel | Email after RP | 2026-08-25 | IWA will continue to do this when requested by the restoration groups, but no group will be required to host an IWA-nominated trustee. The nomination will be made by IWA taking advice as relevant from RDG. RDG is already reviewing where there is an existing right to do this to ensure nominations are up to date. | 2026-08-31 | 1. RDG to review existing nominations to restoration group boards. 2. RDG to review how restoration groups, IWA and wider restoration sector benefit from these nominations - e.g. via a regular nominee discussion. | 2026-08-31
63 | Publishing expertise and guidance - following on from / developing the Technical Restoration Handbook | Email after RP | 2026-08-25 | This will form a key part of the work programme. RP members will be key in determining what guidance is developed / updated. | 2026-08-31 | 1. Focussed discussion on existing guidance, what is useful and what could be added / updated. This will be a general theme in all discussions, but a separate discussion could be arranged to do an initial 'stocktake'. | 2026-08-31
64 | Responding to written questions, distributing answers widely | Email after RP | 2026-08-25 | We will certainly respond to written questions (even if it is to say we do not have the answer), and will endeavour to publish these where possible. | 2026-08-31 | No work programme items.
65 | Placing suitable and skilled IWA members into canal restoration partnerships and ensuring close co-operation with the restoration group(s) represented there | Email after RP | 2026-08-25 | IWA will continue to do this when requested by the restoration partnerships, and where IWA is not currently requested it will generally seek to be invited. The scope of the representatives role and engagement will be somewhat defined by the individual nominated. RDG is reviewing existing nominations in this context and how to ensure that the benefit of these nominations is felt to both the restoration partnerships and the wider sector. | 2026-08-31 | 1. RDG to review existing nominations to restoration partnerships. 2. RDG to review how restoration groups, IWA and wider restoration sector benefit from these nominations - e.g. via a regular nominee discussion. | 2026-08-31
66 | Encouraging restoration groups to focus on end-to-end navigation as the vital element that makes a restoration project come alive and helps it to be economically sustainable and beneficial | Email after RP | 2026-08-25 | It is for individual restoration groups to determine their priorities, as they will best understand what motivates them, their members and their wider communities. IWA will look at how to share best practice in making a restoration economically sustainable, but does not agree that this always follows through a focus on end-to-end navigation. | 2026-08-31 | 1. Focussed discussion on economic generators being considered / developed by restoration groups. | 2026-08-31